## Slide 1
DPO PLATFORM
Direct Phone Outreach Platform
Project Analysis & Plan
Ilia Chigogidze | April 7, 2026

## Slide 2
2 / 20
AGENDA
01
Project Context
Business background & systems overview
02
As-Is Process
10 stages of current workflow & pain points
03
To-Be MVP
Platform solution — 6 streamlined stages
04
Post-MVP Vision
Analytics, dashboards & reporting
05
Project Charter
Goals, KPIs, limitations & risks
06
Project Plan
Timeline, roles & milestones

## Slide 3
3 / 20
PROJECT CONTEXT
The DPO department manages lead generation campaigns. Vendors make phone calls, collect leads, and those leads go through verification before client delivery.
Today, the entire process runs on Google Sheets — dozens of disconnected spreadsheets, manual data entry, and a workflow that doesn't scale.
INFUSE LG
Client & campaign creation
Registry
Client/CID microservice
Google Sheets
Master, Remote, Tracking
MainDB
Initial lead checks
LV / LT
Lead verification & tools
KEY ROLES
Campaign Coordinators · DPO Admin · QC/QA · Vendors · LV Team · Automated Scripts

## Slide 4
4 / 20
AS-IS PROCESS — STAGES 1-3
1
Client & Campaign Creation
CST creates client/campaign in INFUSE LG. CID assigned, synced to Registry.
2
Campaign Initialization
CC creates Word doc with campaign details (goal, GEO, criteria, CQs, ABM lists). Emails to DPO Admin.
Manual Word doc, no validation, emailed around
3
Campaign Setup in Tracking Sheets
DPO Admin manually enters data into Campaign Tracking tab. Creates Master Sheet from template. Configures Settings & Stats tabs.
100% manual data entry, typo-prone

## Slide 5
5 / 20
AS-IS PROCESS — STAGES 4-5
4
Vendor Assignment & Requirements
DPO Admin allocates goal portions to vendors (e.g. V20 gets 100/147 leads)
Creates Remote Google Sheet per vendor per campaign
Sends campaign requirements via email/chat separately
Phone script must be approved before calling starts
Sheet sprawl: 10 campaigns × 3 vendors = 30 Remote sheets + 10 Master sheets
5
Lead Generation & Upload
Vendors call prospects, record conversations, collect lead data
Upload to Remote sheet: name, company, email, title, phone, CQ answers, recording
Auto-copy script moves leads from Remote → Master sheet (works well)
No validation at upload — vendor data quality varies
No upload validation — errors slip through and block downstream

## Slide 6
6 / 20
AS-IS PROCESS — STAGE 6
THE BIGGEST BOTTLENECK
Lead Transfer to MainDB
GAS Script Design (every 1 min):
Check for unprocessed & approved leads on Master sheet
POST /api/lead-upload/dpo → receive partition UUID
Poll GET /api/lead-upload/dpo-status?uuid={uuid} for initial statuses
On error or 10+ failures → stop, set error status
Despite designed automation, CCs also manually copy leads to MainDB.
Manual transfer is still common — slow, error-prone, blocks everything downstream.

## Slide 7
7 / 20
AS-IS PROCESS — STAGES 7-8
7
MainDB Initial Checks
14 initial statuses in 3 categories:
PENDING
Lead valid, moves forward
INIT REJECT
Already exists (Accepted, DPO, In Collection)
REJECTED
Complainer, Unsubscribed, Email not valid, Blacklisted...
Scripts overwrite CC manual corrections
8
Lead Verification — LV/LT
LV Platform (manual):
~30 ov_status values: verified, rejected, questionable, recheck
Leads Tool (automated):
~8 pv_status values: phone, domain, bounce checks
Status Mapping:
30 × 8 = 603 combinations
→ 4 Final Statuses:
Accepted
Rejected
Pending
Returned

## Slide 8
8 / 20
AS-IS PROCESS — STAGES 9-10
9
Status Updates & QA Review
Admin/CC manually triggers status collection
Script calls LVLT: POST /api/contactInfo-by-mails
Fallback: MainDB getDpoStatusByCID or cs-canada-stats
Statuses sync → Master sheet → Remote sheets
QA reviews call recordings manually (16 rejection categories)
10
Rework & Final Delivery
Vendors dispute rejections via sheet comments (unstructured)
DPO Admin manually reviews rework requests
Accepted leads delivered to client
Stats aggregated: Master → All Stats → Campaign/Delivery Tracking
Rework flow is completely unstructured — just comments in a column

## Slide 9
9 / 20
PAIN POINTS SUMMARY
CRITICAL
Manual lead transfer to MainDB — single biggest bottleneck
HIGH PRIORITY
Manual campaign init (Word + email)
Sheet sprawl per campaign/vendor
CC status overwrite conflict
No vendor portal or validation
MEDIUM / POST-MVP
Manual vendor comms (email/chat)
Manual stats aggregation
Manual QA review
Unstructured rework flow
No real-time dashboards

## Slide 10
10 / 20
TO-BE MVP PROCESS
Replacing Google Sheets with a centralized platform
10 stages → 6 stages | Existing MainDB & LV/LT APIs preserved

## Slide 11
11 / 20
TO-BE MVP — STAGES 1-3
1
Platform-Based Campaign Initiation
DPO Admin creates campaign in platform. Pulls Client/CID from Registry API. Enters goal, GEO, criteria, CQs, deadline, ABM list. Auto-populates Campaign Tracking.
REPLACED: Word doc + email + manual sheet entry
2
Vendor Assignment via Platform
Assign vendors, allocate goal portions in-platform. Requirements shared through platform. Limited vendor visibility. Phone script approval built in.
REPLACED: Separate emails/chats + manual Remote sheets
3
Vendor Lead Upload via Platform
Vendors upload through portal with data validation at upload (required fields, format checks, criteria matching). DPO ID & submission date auto-assigned.
REPLACED: Unvalidated Remote sheet entry

## Slide 12
12 / 20
TO-BE MVP — STAGES 4-6
4
Automatic Lead Transfer to MainDB
Platform sends batches via POST /api/lead-upload/dpo automatically. Receives UUID, polls for statuses. 14 MainDB statuses mapped and displayed.
ELIMINATED: Manual 2-4 hour transfer → under 5 minutes
5
Automated Status Collection
Continuous polling via /api/contactInfo-by-mails. Fallback: getDpoStatusByCID / cs-canada-stats. 600+ status combos mapped. CC overwrite conflict resolved — platform is single source of truth.
REPLACED: Manually triggered process → automated continuous polling
6
Campaign Tracking & Reporting
Built-in Campaign Tracking, Delivery Tracking, Stats dashboards. Real-time pacing, percentage metrics. Event-driven notifications (new leads, status changes, reminders).
REPLACED: Formula-based Google Sheet tabs → real-time dashboards

## Slide 13
13 / 20
POST-MVP VISION
Focus: Analytics, Dashboards & Reporting
Phase A
Analytics & Dashboards
Rejection analytics (by reason, vendor, GEO, time)
Vendor performance scoring & leaderboard
Executive dashboard with pipeline forecasting
Phase B
Reporting & Automation
Automated monthly report generation
Ad-hoc report builder (filters, CSV/Excel export)
Historical data migration from Google Sheets
Phase C
Workflow Improvements
Structured rework & dispute resolution
Formal vendor submit → admin review → log history
Out of Scope: Phone call automation | QA recording review workflows

## Slide 14
14 / 20
PROJECT CHARTER — GOALS
1
Reduce lead transfer time from 2-4 hours to under 5 minutes
2
Centralize campaign management — from 3-10+ Google Sheets to zero
3
Automate status collection — manually triggered → continuous polling
4
Vendor portal with data validation — reduce errors by 50%
5
Automate campaign initiation — setup time from 1-2 hours to 15 min
Post-MVP Goals: Rejection analytics · Vendor scoring · Executive dashboards · Automated reporting · Data migration

## Slide 15
15 / 20
CHARTER — RESULTS & LIMITATIONS
MVP RESULTS (Deliverables)
Centralized DPO Platform web application
Automated lead push to MainDB via API
Automated status collection (14 + 600+ mappings)
Campaign & Delivery Tracking dashboards
Role-based access (Admin, CC, QC/QA, Vendor)
Automated notification system
LIMITATIONS (Out of Scope)
Will NOT modify INFUSE LG, Registry, or MainDB
Will NOT change LV/LT verification process
No client portal
Vendor recruitment/contracts/billing excluded
Historical data migration → Post-MVP
Phone automation & QA review → out of scope

## Slide 16
16 / 20
PROJECT CHARTER — KPIs
KPI | Before | After (Target)
Lead transfer time / batch | 2-4 hours (manual) | < 5 minutes (auto)
Google Sheets / campaign | 3-10+ sheets | 0 sheets
Status collection | Manually triggered | Automated polling
Lead data errors at upload | ~15-20% (no validation) | 50% reduction
Campaign setup time | 1-2 hours manual | < 15 minutes
Post-MVP KPIs
Monthly report generation
4-6 hours manual
Fully automated
Rejection root-cause analysis
Manual per campaign
Automated dashboard
Vendor performance visibility
No scoring
Composite scores + leaderboard

## Slide 17
17 / 20
PROJECT CHARTER — RISKS
Risk | Type | Prob | Impact | Mitigation
LV/LT & MainDB APIs behave unexpectedly | Technical | Med | High | Early API testing, sandbox in sprint 1
MainDB lead push differs from docs | Technical | Med | Med | Postman collections, manual fallback
600+ status mapping errors | Technical | High | Med | Mapping review + automated tests
Vendor resistance to new platform | Org | Med | Med | UAT involvement, parallel run, training
Stakeholder availability gaps | Org | Med | Med | Recurring meetings, async reviews
Scope creep from new requirements | Schedule | High | High | Clear MVP scope, change request process
Data integrity during transition | Data | Low | High | Parallel run + reconciliation checks

## Slide 18
18 / 20
PROJECT PLAN — TIMELINE
Pre-MVP
4 weeks
May 4 – Jun 1
MVP
~20 weeks
Jun 1 – Oct 16
Post-MVP
~15 weeks
Oct 19 – Jan 30, 2027
MVP Phase Breakdown:
Design
3 wks
Architecture, UI/UX wireframes, status mapping spec
Backend
9 wks
Campaign init, vendor mgmt, lead upload, MainDB, LV/LT, notifications, RBAC
Frontend
8 wks
Campaign UI, vendor portal, dashboards, lead views (overlaps backend)
Testing
ongoing
Unit/integration, E2E, 2-week UAT
Deploy
3 wks
Staging, production (2-3 pilot campaigns), training, parallel ops
Buffer
2 wks
10% contingency for schedule risk
TOTAL PROJECT: ~9 months (May 2026 – January 2027)

## Slide 19
19 / 20
ROLES & KEY MILESTONES
RACI Roles
Project Manager
Planning, charter, timeline, training
Business Analyst
Requirements, process docs, mapping
Team
Backend, frontend, testing, deployment
Design Owner
UI/UX wireframes, prototypes
Product Owner
Feature prioritization, scoring
Sponsor/Customer
Charter approval, UAT, validation
Key Milestones
Jun 1
Charter & Plan approved / Kickoff
Jun 19
Design phase complete
Aug 14
Backend development complete
Aug 28
Frontend development complete
Sep 18
UAT complete
Oct 2
MVP go-live
Oct 16
MVP phase closed
Jan 16
Post-MVP features deployed
Jan 30
Post-MVP phase closed

## Slide 20
SUMMARY
Replaces fragmented Google Sheets workflow with a centralized platform
MVP eliminates the biggest bottleneck — manual lead transfer — and automates campaign init, vendor management, status collection & dashboards
Post-MVP builds analytics, reporting & vendor intelligence on top of the MVP foundation
~9 months | Clear scope boundaries | Quantifiable KPIs | Identified risks with mitigation
Thank You
20 / 20