## Plan
Step | State | Start date | End date | Responsible | Comments
Pre-MVP: Planning & Analysis
Requirements gathering & stakeholder interviews | Not started | 2026-05-04 | 2026-05-15 | Project Manager, Business Analyst | Interviews with CC, DPO Admin, QC/QA, Vendors; clarify open questions from instructions
As-Is process documentation & pain points analysis | Not started | 2026-05-11 | 2026-05-22 | Business Analyst | Document all 10 stages, 12 pain points, data flows; validated with stakeholders
To-Be MVP & Post-MVP process design | Not started | 2026-05-18 | 2026-05-29 | Business Analyst, Project Manager | Define 6 MVP stages, scope boundaries, Post-MVP roadmap
Technical feasibility assessment | Not started | 2026-05-18 | 2026-05-29 | Team | Review Registry API, MainDB endpoints (Postman), LV/LT /api/contactInfo-by-mails endpoint
Project Charter & Plan approval | Not started | 2026-05-25 | 2026-06-01 | Project Manager, Sponsor/Customer | Sign-off from project sponsor and key stakeholders
MVP Phase
Design
System architecture & data model design | Not started | 2026-06-01 | 2026-06-12 | Team, Design Owner | DB schema, API contracts, integration patterns with Registry/MainDB/LV/LT
UI/UX wireframes & prototypes | Not started | 2026-06-01 | 2026-06-19 | Design Owner | Campaign mgmt, vendor portal, admin dashboards, lead upload flow; user testing with CC and vendors
Status mapping specification | Not started | 2026-06-08 | 2026-06-19 | Business Analyst, Team | Map all 600+ LV/LT status combinations and 14 MainDB statuses to 4 final statuses
Backend Development
Campaign initiation module + Registry integration | Not started | 2026-06-15 | 2026-07-03 | Team | Pull clients/CIDs from Registry; campaign creation form; auto-populate Campaign Tracking
Vendor assignment & requirements management | Not started | 2026-06-22 | 2026-07-10 | Team | Goal allocation, requirements sharing, phone script approval workflow
Lead upload API + data validation | Not started | 2026-07-06 | 2026-07-24 | Team | Vendor lead upload with real-time validation; DPO ID auto-assign
MainDB integration (lead push + initial statuses) | Not started | 2026-07-13 | 2026-07-31 | Team | POST /api/lead-upload/dpo, GET dpo-status polling, 14 MainDB status mapping
LV/LT status collection integration | Not started | 2026-07-27 | 2026-08-14 | Team | Integration with existing /api/contactInfo-by-mails; fallback to getDpoStatusByCID; full status mapping
Notification & alerting system | Not started | 2026-08-03 | 2026-08-14 | Team | Event-driven notifications: new leads, status changes, overdue reviews, CC reminders
Role-based access control (RBAC) | Not started | 2026-07-06 | 2026-07-17 | Team | 4 roles: DPO Admin, CC, QC/QA, Vendor; permission matrix per feature
Frontend Development
Campaign management UI | Not started | 2026-07-06 | 2026-07-31 | Team, Design Owner | Campaign list, creation form, campaign detail view, settings
Vendor portal | Not started | 2026-07-20 | 2026-08-07 | Team, Design Owner | Vendor view: assigned campaigns, lead upload form, status tracking; limited visibility
Admin dashboards (Campaign Tracking + Delivery Tracking) | Not started | 2026-07-27 | 2026-08-21 | Team, Design Owner | Replace Google Sheet tabs; real-time stats, pacing, % metrics, unallocated calc
Lead management & status views | Not started | 2026-08-10 | 2026-08-28 | Team, Design Owner | Lead list with filtering, status history, audit trail, manual override with logging
Testing
Unit & integration testing | Not started | 2026-07-13 | 2026-09-04 | Team | Ongoing during development; API tests, status mapping validation, MainDB/LV integration tests
End-to-end system testing | Not started | 2026-08-31 | 2026-09-11 | Team | Full campaign lifecycle: initiation → vendor upload → MainDB → LV/LT → status sync → dashboards
User Acceptance Testing (UAT) | Not started | 2026-09-07 | 2026-09-18 | Sponsor/Customer, Team | Real users test with representative campaigns; collect feedback; fix critical issues
Deployment & Launch
Staging deployment & smoke testing | Not started | 2026-09-14 | 2026-09-18 | Team | Deploy to staging; run regression suite; performance baseline
Production deployment | Not started | 2026-09-21 | 2026-09-25 | Team, Project Manager | Phased rollout; start with 2-3 pilot campaigns
User training & documentation | Not started | 2026-09-14 | 2026-09-25 | Project Manager, Business Analyst | Training sessions for CC, DPO Admin, vendors; user guides; video walkthroughs
Parallel operation & monitoring | Not started | 2026-09-21 | 2026-10-02 | Project Manager, Sponsor/Customer | Run platform alongside Google Sheets for 1-2 weeks; data reconciliation checks
MVP contingency buffer (10%) | Not started | 2026-10-05 | 2026-10-16 | Project Manager | ~2 weeks buffer for delays, bug fixes, scope adjustments (10% of ~20 week MVP)
Post-MVP Phase
Analytics & Dashboards
Advanced rejection analytics dashboard | Not started | 2026-10-19 | 2026-11-13 | Team, Business Analyst | Rejection breakdown by reason, vendor, GEO, time period; trend analysis; drill-down filters
Vendor performance scoring system | Not started | 2026-11-02 | 2026-11-27 | Team, Product Owner | Composite score: acceptance rate, quality, timeliness; vendor leaderboard; allocation recommendations
Executive dashboard & pipeline health | Not started | 2026-11-16 | 2026-12-11 | Team, Business Analyst | Pipeline health indicators, campaign forecasting, pacing trends, goal attainment tracking
Historical data migration from Google Sheets | Not started | 2026-11-23 | 2026-12-11 | Team, Business Analyst | Migrate key historical campaign data for trend baseline and analytics continuity
Reporting & Automation
Automated monthly reporting | Not started | 2026-12-01 | 2026-12-18 | Team | Scheduled report generation; email distribution to stakeholders; customizable templates
Ad-hoc report builder | Not started | 2026-12-08 | 2026-12-25 | Team, Design Owner | User-configurable reports with filters, date ranges, groupings; CSV/Excel export
Workflow Improvements
Rework/dispute resolution system | Not started | 2026-12-15 | 2027-01-09 | Team, Design Owner | Structured rework workflow: vendor dispute UI, admin review queue, resolution history
Post-MVP testing & deployment | Not started | 2027-01-05 | 2027-01-16 | Team | Regression testing, UAT for new features, production deployment
Post-MVP contingency buffer (10%) | Not started | 2027-01-19 | 2027-01-30 | Project Manager | ~2 weeks buffer (10% of ~13 week Post-MVP phase)